## MVP Tracker
Tender Smiles Healthcare Staffing — MVP Tracker
Last updated: 16 April 2026
# | Area | Task / Item | Status | Notes | Priority
1 | Landing Page | Navbar (logo, nav links, phone, CTA) | ✅ Done | Fully built and responsive | Medium
2 | Landing Page | Hero section (headline, image, CTAs) | ✅ Done | Stock image from Unsplash | Medium
3 | Landing Page | Stats bar (24/7, 100% screened, <24h) | ✅ Done | Static values | Low
4 | Landing Page | About section (text + image) | ✅ Done | Copy and image in place | Low
5 | Landing Page | Services section (4 service cards) | ✅ Done | Temporary, Direct Hire, Per Diem, Locum Tenens | Low
6 | Landing Page | Why Choose Us section | ✅ Done | 3 feature cards + mission/vision | Low
7 | Landing Page | Contact bar (phone, email, address) | ✅ Done | Real contact details in code | Low
8 | Landing Page | Footer with links | ✅ Done | Copyright year says 2024 — needs updating | Low
9 | Form — Apply | Form UI (name, email, phone, message) | ✅ Done | Styled, responsive | Medium
10 | Form — Apply | CV file upload (PDF/DOC/DOCX, max 10MB) | ✅ Done | Drag-style button, file preview | Medium
11 | Form — Apply | Client-side validation + inline errors | ✅ Done | All fields validated on submit & blur | Medium
12 | Form — Apply | Loading / success / error states | ✅ Done | Spinner, success card, error banner | Medium
13 | Form — Find Staff | Form UI (org, contact, role, headcount, date) | ✅ Done | All fields built | Medium
14 | Form — Find Staff | Client-side validation + inline errors | ✅ Done | Required fields validated | Medium
15 | Form — Find Staff | Loading / success / error states | ✅ Done | Same pattern as apply form | Medium
16 | Backend | Express server with /api/apply endpoint | ✅ Done | Accepts multipart form + CV attachment | High
17 | Backend | Express server with /api/request-staff endpoint | ✅ Done | Sends JSON email to recipient | High
18 | Backend | Multer file handling (CV attachment) | ✅ Done | Stores in memory, attaches to email | High
19 | Backend | Nodemailer email sending logic | ✅ Done | Both endpoints wired up | High
20 | Backend | SMTP credentials in .env file | 🔧 Needs Config | .env exists but has placeholder values — must fill in real host, user, password | Critical
21 | Backend | RECIPIENT_EMAIL in .env | 🔧 Needs Config | Set to "hiring@yourdomain.com" — must be customer's real inbox | Critical
22 | Backend | Start the Express server before the site works | ⚠️ Partial | Run "npm run server" in a second terminal — or add "concurrently" to run both at once | Critical
23 | Backend | CORS origin hardcoded to localhost:5173 | ⚠️ Partial | Will break in production — must update to real domain before deploying | High
24 | Frontend | API URLs hardcoded to http://localhost:3001 | ⚠️ Partial | Two fetch() calls in App.jsx point to localhost — must change to real server URL for production | High
25 | Deployment | Choose and set up hosting for the frontend | ❌ Not Started | Recommended: Vercel or Netlify (free) | Critical
26 | Deployment | Choose and set up hosting for the Express backend | ❌ Not Started | Recommended: Render free tier or Railway (~$5/mo) | Critical
27 | Deployment | Buy and connect a domain name | ❌ Not Started | Recommended: Namecheap (~$10–15/year) | High
28 | Deployment | Update CORS + API URLs for production domain | ❌ Not Started | After hosting is chosen, update both files | High
29 | Email | Test end-to-end email delivery | ❌ Not Started | Submit both forms, confirm emails arrive with CV attached | Critical
30 | Polish | Update footer copyright year from 2024 to 2025 | ❌ Not Started | Minor but looks unprofessional | Low
Summary
Status | Count
✅ Done
🔧 Needs Config
⚠️ Partial
❌ Not Started
Total